## Sheet1
SDC Learning Portal Test Suite
Test Suite Version : 1.0
Test Suite Developed By: Huzaifa
Tests Executed By: Huzaifa | [9 empty] | Re-run: node tests/suite.run.js <local URL> (Oct 2026)
[10 empty] | Status | Actual Result / Notes | Executed
Test Case ID | Module | Test Scenario | Preconditions | Test Steps | Test Data | Expected Result | Priority | Test Type | Reference
TC-001 | Authentication | Successful login with default Admin credentials | User is on login.html; local storage initialized with seed data | 1. Enter admin email in email field. 2. Enter admin password. 3. Click "Sign In" button. | Email: admin@sdclearn.demo, Password: Demo@123 | User is authenticated successfully and redirected to /dashboard with full staff admin console. | High | Functional / Positive | IMPLEMENTATION-Authentication, BRD-FR-B2 | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-002 | Authentication | Successful login with default Instructor credentials | User is on login.html; instructor account exists in seed data | 1. Enter instructor email. 2. Enter instructor password. 3. Click "Sign In". | Email: instructor@sdclearn.demo, Password: Demo@123 | User is authenticated and navigated to the instructor console view with assigned courses. | High | Functional / Positive | IMPLEMENTATION-Roles & permissions, BRD-FR-I1 | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-003 | Authentication | Successful login with default Learner credentials | User is on login.html; learner account exists in seed data | 1. Enter learner email. 2. Enter learner password. 3. Click "Sign In". | Email: learner@sdclearn.demo, Password: Demo@123 | User is redirected directly to /courses ("My Courses" SDI-style portal view). | High | Functional / Positive | BRD-FR-L1, IMPLEMENTATION-Roles & permissions | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-004 | Authentication | Validation on invalid password entry | User is on login.html | 1. Enter valid learner email. 2. Enter wrong password. 3. Click "Sign In". | Email: learner@sdckarachi.org.pk, Password: wrongpassword123 | Error notification/toast appears indicating invalid credentials; session is not created. | High | Functional / Negative | IMPLEMENTATION-Authentication | PASS | Used learner@sdclearn.demo (the sheet's learner@sdckarachi.org.pk is not a seeded account). Message: "Email or password is incorrect." | Automated (tests/suite.run.js)
TC-005 | Authentication | Validation on non-existent email address | User is on login.html | 1. Enter an unregistered email. 2. Enter any password. 3. Click "Sign In". | Email: ghost@sdckarachi.org.pk, Password: password123 | Error message displayed indicating account does not exist or credentials invalid; login fails. | High | Functional / Negative | IMPLEMENTATION-Authentication | PASS | Same generic message as a wrong password, by design (does not reveal which emails exist). | Automated (tests/suite.run.js)
TC-006 | Authentication | Quick demo role switcher shortcuts | User is on login.html | 1. Click on the "Admin" demo quick-fill chip/button. 2. Verify fields populate. 3. Click "Sign In". | Demo chip: Admin | Email and password populate automatically; user signs in directly to the Admin console. | Medium | Functional / Positive | IMPLEMENTATION-File map (login.js) | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-007 | Authentication | Password reset informational prompt display | User is on login.html | 1. Locate and click "Forgot Password" or reset info link. | Action: Click reset link | Informational modal or text appears instructing the user to contact the SDC Karachi coordinator at sdckar@sdckarachi.org.pk. | Low | UI / Functional | IMPLEMENTATION-File map (login.js), BRD-FR-B5 | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-008 | Authentication | Inactive/suspended user login rejection | User exists with status: 'inactive' in store | 1. Enter credentials of the inactive user. 2. Click "Sign In". | Status: inactive user credentials | Login is blocked with a message stating the account is inactive/disabled. | High | Functional / Negative | IMPLEMENTATION-Data model (users.status) | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-009 | Authentication | User session persistence across browser reloads | User is logged in as Learner on #/courses | 1. Refresh the browser page (F5/Cmd+R). 2. Check the active view and user session state. | Refresh on app.html#/courses | Session is retained without redirecting back to login.html; user remains on #/courses. | High | Functional / Session | IMPLEMENTATION-Architecture | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-010 | Authentication | User logout and session termination | User is logged in to app.html | 1. Click the user profile / header dropdown. 2. Click "Sign Out" / "Logout". | Action: Click Logout | Active session token/state is cleared from storage; user is redirected to login.html. | High | Functional / Session | BRD-FR-L5, IMPLEMENTATION-Architecture | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-011 | Authorization | Direct URL access prevention for unauthenticated users | Browser is unauthenticated with cleared local session | 1. Directly navigate to app.html#/dashboard. 2. Observe redirection and storage handling. | URL: app.html#/dashboard | App router blocks access and redirects user to login.html. | High | Security / Authorization | IMPLEMENTATION-Routing and pages | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-012 | Authorization | Role-based route restriction: Learner accessing Admin Dashboard | User logged in as Learner (base: student) | 1. Manually enter hash route app.html#/dashboard or #/settings in address bar. 2. Press Enter. | URL: app.html#/dashboard | Router enforces permission check (App.allowed()); denies access and redirects to allowed page (/courses) or shows unauthorized toast. | High | Security / Authorization | IMPLEMENTATION-Roles & permissions | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-013 | Authorization | Role-based route restriction: Instructor accessing System Settings | User logged in as Instructor (base: teacher) | 1. Enter hash route app.html#/settings in address bar. 2. Press Enter. | URL: app.html#/settings | Access denied due to lack of settings:view permission; route redirection or 403-state rendered. | High | Security / Authorization | IMPLEMENTATION-Roles & permissions | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-014 | Branding & UI | Verify SDC Karachi visual branding and absence of "EAD University" | User is on login.html and app.html | 1. Inspect logo, header titles, meta tags, and footer across all pages. 2. Search page DOM for strings "EAD" or "EAD University". | Global DOM inspection | SDC Karachi branding, crest logo, and council contact info displayed; zero occurrences of "EAD University". | High | UI / Branding | BRD-FR-B1, BRD-FR-B2, BRD-FR-B4 | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-015 | Branding & UI | Verify institutional contact details in footers and contact strips | User logged in on app.html | 1. Scroll to the footer of any dashboard or public view. 2. Verify phone numbers, official email, and website link. | Text verification | Shows (021) 99334387, 99334388, sdckar@sdckarachi.org.pk, and link to sdckarachi.org.pk. | Medium | UI / Branding | BRD-FR-B5 | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-016 | Branding & UI | Light and Dark theme toggle switching | User logged in on any view in app.html | 1. Click theme toggle button in header. 2. Verify body classes, CSS variables, and contrast. 3. Toggle back. | Theme toggle click | Application switches between light and dark themes seamlessly; CSS variables update; preference persists in sdcTheme. | Medium | UI / Functional | BRD-FR-B3, BRD-NFR-3, IMPLEMENTATION-Key flows | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-017 | Branding & UI | Responsive layout check on mobile viewport | User logged in as Learner on app.html | 1. Set viewport to 375x667 (iPhone SE). 2. Verify sidebar collapses into mobile drawer. 3. Inspect session cards, header tools, and tables. | Viewport: 375px width | Layout collapses neatly without horizontal overflow; top bar, Zoom tool, and session list remain fully legible and clickable. | Medium | UI / Responsive | BRD-NFR-2, BRD-10 (Criteria 10) | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-018 | Learner Portal | "My Courses" list rendering | User logged in as Learner with enrolled courses | 1. Navigate to #/courses. 2. Check course cards rendered. | Course: "Microsoft Excel with AI-Driven Analytics" | Displays course card with title, tagline, session count, level badge, and color accent. | High | Functional / Positive | BRD-FR-L1, BRD-6.2 | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-019 | Learner Portal | Search and filter courses on "My Courses" | User on #/courses with multiple seeded courses | 1. Type "Excel" in search box. 2. Type non-matching string "Photoshop". 3. Clear search box. | Queries: Excel, Photoshop, empty | Search instantly filters cards to matching course; non-matching query displays empty state; clearing restores all courses. | Medium | Functional / Search | BRD-FR-L1, IMPLEMENTATION-pages-learn.js | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-020 | Learner Portal | Empty state when Learner has no enrolled courses | Learner with 0 enrollments logged in | 1. Log in as a learner with empty enrollment list. 2. View #/courses. | Learner: zero enrollments | Displays friendly empty state: "No courses enrolled yet" with guidance to contact administration. | Medium | UI / Edge Case | BRD-FR-L9 | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-021 | Learner Portal | Navigate from Course Card to Course Home | User on #/courses | 1. Click on a course card (e.g., Excel Analytics). 2. Verify URL and rendered components. | Course ID: course-excel-01 | Navigates to #/course/:id; renders course header, top buttons (Outline, Submit), and ordered list of sessions. | High | Functional / Navigation | BRD-FR-L2, BRD-FR-L3 | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-022 | Learner Portal | Course Home displays "Course Outline" and "Submit Assignment" action bar | User on #/course/:id | 1. Verify action buttons near top of course home page. | Route: #/course/:id | Prominent buttons for "Course Outline" and "Submit Assignment" are pinned/visible near the top. | Medium | UI / Functional | BRD-FR-L3 | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-023 | Learner Portal | View Course Outline / Module Roadmap | User on #/course/:id | 1. Click "Course Outline" button. 2. Verify modules, prerequisites, outcomes, and syllabus. | Route: #/outline | Course outline page renders structured modules, learning outcomes, syllabus topics, and delivery details. | Medium | Functional / Positive | BRD-FR-L4, IMPLEMENTATION-pages-learn.js | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-024 | Learner Portal | Session list status badge calculations | User on #/course/:id | 1. Observe badges next to each session item: past, current day, and future sessions. | Dates: Yesterday, Today, Tomorrow | Past sessions show "Available" or "Completed"; today's session shows "Today"; future sessions show "Upcoming". | High | Business Logic | BRD-FR-L2, IMPLEMENTATION-Key flows | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-025 | Learner Portal | Access individual Session Details page | User on #/course/:id | 1. Click on an available session item in list. 2. Verify route and components. | Session ID: sess-01 | Navigates to #/session/:sid; displays breadcrumb, session title, date/time, summary, video area, resources, and next/prev nav. | High | Functional / Navigation | BRD-FR-L4 | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-026 | Learner Portal | Previous and Next session navigation buttons | User on #/session/:sid (Session 2 of multi-session course) | 1. Click "Previous Session" button. 2. Verify Session 1 opens. 3. Click "Next Session" twice. 4. Verify Session 3 opens. | Sessions 1, 2, 3 | Smoothly navigates to preceding and succeeding session details; first session disables "Previous", last disables "Next". | Medium | Functional / Navigation | BRD-FR-L4 | PASS | At the ends the button is hidden (first session) or becomes "Back to course" (last session) rather than shown disabled. | Automated (tests/suite.run.js)
TC-027 | Learner Portal | Embedded video rendering (YouTube embed) | User on #/session/:sid with YouTube video URL | 1. Inspect video player region for a session configured with a YouTube URL. | URL: https://www.youtube.com/watch?v=... | Iframe renders YouTube embed cleanly with responsive aspect ratio. | Medium | Functional / Media | BRD-FR-L4, IMPLEMENTATION-Key flows | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-028 | Learner Portal | Direct HTML5 video playback (.mp4 / .webm) | User on #/session/:sid with direct video URL | 1. Inspect session configured with .mp4 link. | URL ending in .mp4 | Native <video> player element renders with controls (play, pause, volume, fullscreen). | Medium | Functional / Media | IMPLEMENTATION-Key flows | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-029 | Learner Portal | Fallback link for non-embeddable video providers | User on #/session/:sid with external custom URL | 1. Open session with custom external link (e.g. cloud drive link). | URL: generic external link | Displays "Open recording in new tab" external CTA button instead of broken iframe. | Low | Functional / Fallback | IMPLEMENTATION-Key flows | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-030 | Learner Portal | Session Resources listing and download trigger | User on #/session/:sid with attached materials | 1. Scroll to "Session Resources" panel. 2. Verify resource titles, file types, and size tags. 3. Click download link. | Resource: Session1_Datasets.xlsx | File download initiates or opens the asset path (assets/resources/...); no broken URLs. | High | Functional / Download | BRD-FR-L4, IMPLEMENTATION-File map | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-031 | Learner Portal | Empty state for session with no resources attached | User on a session with resources: [] | 1. Open session detail having empty resources array. | resources: [] | Displays polite info badge: "No resources attached to this session yet". | Low | UI / Edge Case | BRD-FR-L9 | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-032 | Learner Portal | Zoom tool popover / modal launch from header | User on #/course/:id or #/session/:sid | 1. Click "Zoom Live Class" tool button in top header bar. | Course Zoom configuration | Zoom panel opens displaying Join/Register URL, Meeting ID, Passcode, and copy-to-clipboard action buttons. | High | Functional / Live Class | BRD-FR-L5, BRD-FR-L6 | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-033 | Learner Portal | Copy Meeting ID and Password from Zoom panel | User has Zoom panel modal opened | 1. Click "Copy Meeting ID" button. 2. Click "Copy Passcode" button. | Zoom credentials | Clipboard receives the exact text; toast appears confirming "Meeting ID copied" / "Passcode copied". | Medium | Functional / UI | BRD-FR-L6 | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-034 | Learner Portal | Help tool launch from header | User on any course page in Learner portal | 1. Click "Help / Support" button in header bar. | Configured helpUrl | Opens the configured support URL (Google Form or contact route) in a new browser tab. | Medium | Functional / External Link | BRD-FR-L5, BRD-FR-L7 | PASS | Fixed: the Help button was labelled "Open support form" even when it opened an email. It now says "Email support" for the default mailto link and opens a configured form URL in a new tab. | Automated (tests/suite.run.js)
TC-035 | Learner Portal | Submit Assignment CTA from session details | User on #/session/:sid that has an associated assignment | 1. Click "Submit Assignment" CTA button within session detail view. | Associated assignment ID | Navigates to #/submit with course and session pre-selected in the form dropdowns. | High | Functional / Navigation | BRD-FR-L4, BRD-FR-L8 | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-036 | Learner Portal | Valid assignment file submission (Client / Express) | User on #/submit; enrolled in active course | 1. Select session and assignment. 2. Confirm learner email. 3. Drag & drop or select an Excel file (.xlsx, 2MB). 4. Click "Submit Assignment". | File: project_submission.xlsx, Size: 2MB | File uploads successfully via POST /api/lms/uploads (or inline fallback); status sets to "Submitted"; confirmation toast shown. | High | Functional / Upload | BRD-FR-L8, IMPLEMENTATION-Key flows | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-037 | Learner Portal | Assignment submission rejection for invalid file extension | User on #/submit | 1. Choose assignment. 2. Select an executable or unsupported file (.exe or .bat). 3. Attempt to submit. | File: payload.exe | Client validation immediately prevents upload; error banner specifies allowed formats (.xlsx, .docx, .pptx, .pdf, .pbix, .ipynb, .sql, .txt). | High | Validation / Security | BRD-FR-L8, BRD-NFR-7 | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-038 | Learner Portal | Assignment submission rejection for file exceeding size limit | User on #/submit | 1. Select assignment. 2. Attach a file larger than 30MB. 3. Attempt to upload. | File: huge_dataset.zip (35MB) | System rejects upload; displays error that file exceeds maximum permitted size of 30MB. | High | Validation / Boundary | BRD-FR-L8, BRD-NFR-7 | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-039 | Learner Portal | Replace previous un-graded assignment submission | Learner has an existing submission with status "Submitted" | 1. Navigate to #/submit for the same assignment. 2. Upload a revised file (revision_v2.xlsx). 3. Click Submit. | File: revision_v2.xlsx | New submission replaces current active record; previous record preserved in history array; toast confirms update. | High | Business Logic | BRD-FR-L8, IMPLEMENTATION-Data model (submissions.history) | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-040 | Learner Portal | Block assignment replacement after submission is graded | Learner submission status is "Graded" | 1. Navigate to #/submit for the graded assignment. 2. Attempt to upload new file. | Status: Graded | Form blocks upload button and displays alert: "This assignment has already been graded and cannot be replaced". | High | Business Logic / Security | IMPLEMENTATION-Key flows (Submissions) | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-041 | Learner Portal | Late assignment submission behavior when lateAllowed: false | Assignment due date is in the past; lateAllowed set to false | 1. Navigate to #/submit for expired assignment. 2. Attempt to submit file. | Due date: Yesterday, lateAllowed: false | Submission is blocked; system notifies user that the deadline has passed and late submissions are closed. | Medium | Business Logic | IMPLEMENTATION-Key flows, Data model | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-042 | Learner Portal | Late assignment submission behavior when lateAllowed: true | Assignment due date is in the past; lateAllowed set to true | 1. Upload file for past-due assignment. 2. Submit file. | Due date: Yesterday, lateAllowed: true | File is accepted; submission status is flagged as "Late" with timestamp recorded. | Medium | Business Logic | IMPLEMENTATION-Key flows | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-043 | Learner Portal | Learner "My Assignments" overview page | User logged in as Learner | 1. Navigate to #/assignments from main menu. 2. Check list of all assignments across enrolled courses. | Route: #/assignments | Table displays assignment title, course, due date, submission status (Submitted/Pending/Graded), and received grade. | Medium | Functional / Positive | IMPLEMENTATION-File map (pages-learn.js) | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-044 | Learner Portal | Learner Training Calendar view | User logged in as Learner | 1. Navigate to #/calendar from menu. | Route: #/calendar | Calendar renders scheduled sessions, batch start dates, and assignment deadlines for enrolled courses. | Medium | Functional / Positive | BRD-3.2, IMPLEMENTATION-File map | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-045 | Learner Portal | Session access control for Restricted Mode enrollment | Learner enrolled with accessMode: 'restricted' and limited allowedSessionIds | 1. Log in as restricted learner. 2. Navigate to course session list. 3. Attempt to open a session not in allowedSessionIds. | Non-permitted session ID | Session displays "Locked" badge; clicking shows access restricted message preventing video/material viewing. | High | Security / Business Logic | BRD-3.2, IMPLEMENTATION-Key flows | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-046 | Learner Portal | Progress tracking percentage update on session completion | Learner enrolled in course with 4 sessions | 1. Check initial progress bar on course card. 2. Open and complete an unviewed session. 3. Return to course dashboard. | 1 out of 4 sessions marked completed | Progress percentage increases by 25%; progress collection in sdcLearnDB_v1 updates completedSessionIds. | Medium | Business Logic | BRD-3.2, IMPLEMENTATION-Data model (progress) | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-047 | Learner Portal | Mid-course Learner Feedback submission | Learner actively enrolled in course | 1. Open course feedback modal/section. 2. Enter star rating (1-5). 3. Enter testimonial comment. 4. Click Submit Feedback. | Rating: 5, Comment: "Excellent practical hands-on exercises." | Feedback saved to feedback collection; confirmation toast displayed; learner prevented from duplicate spamming. | Low | Functional / Positive | BRD-FR-L10, IMPLEMENTATION-Data model (feedback) | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-048 | Learner Portal | Learner Attendance History view | User logged in as Learner | 1. Navigate to #/attendance (or Attendance tab in Learner portal). | Route: #/attendance | Displays session-by-session attendance records (Present, Late, Absent, Excused) and overall attendance percentage. | Medium | Functional / Positive | BRD-4, BRD-5, IMPLEMENTATION-Data model | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-049 | Learner Portal | Learner View Results and Marks breakdown | Results published for Learner's enrolled course | 1. Navigate to #/results. 2. Inspect course grading card. | Published results record | Displays assignment average, assessment marks, attendance %, final combined %, and assigned letter grade. | High | Functional / Positive | IMPLEMENTATION-pages-ops.js | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-050 | Learner Portal | Learner Certificate download/view trigger | Learner has an issued certificate with status "Valid" | 1. Navigate to #/certificates. 2. Locate eligible course. 3. Click "View Certificate" / "Download". | Certificate Code: SDC-2026-0001 | Certificate display modal or printable view opens with official SDC Karachi credentials and verification code. | High | Functional / Positive | BRD-BO-6, IMPLEMENTATION-pages-ops.js | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-051 | Public Verification | Public Certificate Verification - Valid Code | Public user on verify.html (unauthenticated) | 1. Open verify.html. 2. Enter valid certificate code in input box. 3. Click "Verify Certificate". | Code: SDC-2026-0001 | System displays verification card: Learner Name, Course Title, Issue Date, Grade, and green "Valid Certificate" badge. | High | Functional / Public | BRD-BO-6, BRD-3.2, IMPLEMENTATION-File map (verify.html) | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-052 | Public Verification | Public Certificate Verification - Revoked Code | Public user on verify.html | 1. Enter certificate code that has status: 'Revoked'. 2. Click "Verify Certificate". | Code of revoked certificate | System displays warning badge stating the certificate was revoked by SDC Karachi administration. | High | Functional / Negative | IMPLEMENTATION-Data model (certificates.status) | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-053 | Public Verification | Public Certificate Verification - Invalid / Non-existent Code | Public user on verify.html | 1. Enter random code INVALID-9999-XXXX. 2. Click "Verify Certificate". | Code: INVALID-9999-XXXX | Error alert renders: "No certificate found matching this verification code. Please check your credentials." | Medium | Functional / Negative | IMPLEMENTATION-File map (verify.html) | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-054 | Instructor Portal | Instructor Courses dashboard filtering | User logged in as Instructor | 1. Navigate to #/courses or #/manage/courses. 2. Check visible courses. | Instructor ID: inst-01 | Only courses where instructorIds includes the logged-in instructor are listed (courseScope: 'assigned'). | High | Security / Filtering | IMPLEMENTATION-Roles & permissions | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-055 | Instructor Portal | Instructor Session Builder - Add New Session | Instructor on course builder #/manage/course/:id?tab=sessions | 1. Click "Add Session". 2. Fill Order, Title, Date, Time, Duration, Module, Summary. 3. Enter Video URL. 4. Click Save. | Title: "Session 4: Power Query Transformations", Date: upcoming date | New session record is appended to sessions collection and instantly reflects in course session outline. | High | Functional / CRUD | BRD-FR-I4, IMPLEMENTATION-pages-manage.js | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-056 | Instructor Portal | Instructor Resource Upload - Add Session Material | Instructor on course builder sessions tab | 1. Open session editor modal. 2. In Resources section, click "Attach Resource". 3. Provide Title and select file (Sample_Query.xlsx). 4. Save session. | Resource: Sample_Query.xlsx | Resource entry added to session.resources array; available for learner download. | High | Functional / Upload | BRD-FR-I2, IMPLEMENTATION-pages-manage.js | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-057 | Instructor Portal | Instructor Mark Attendance | Instructor on #/attendance | 1. Select assigned course and specific session. 2. Mark learners as "Present", "Absent", "Late". 3. Add optional notes. 4. Click "Save Attendance". | Session: sess-01, Statuses: Mixed | Attendance records saved to attendance collection; success toast confirms persistence; learner attendance % updates. | High | Functional / CRUD | BRD-FR-I2, IMPLEMENTATION-pages-ops.js | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-058 | Instructor Portal | Instructor Submissions Review and Grading | Instructor on #/submissions | 1. Filter submissions by assigned course. 2. Click on a learner's submitted assignment. 3. Download/inspect file. 4. Enter Marks (e.g. 85/100) and Feedback comments. 5. Click "Save Grade". | Marks: 85, Feedback: "Good DAX formulas, fix date table." | Submission status updates to "Graded"; grade and feedback saved; learner notified. | High | Functional / CRUD | BRD-FR-I2, IMPLEMENTATION-pages-ops.js | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-059 | Instructor Portal | Instructor Publish Course Announcement | Instructor on #/announcements | 1. Click "New Announcement". 2. Select Audience: "Enrolled Course Learners". 3. Select Course. 4. Enter Title and Announcement Message. 5. Click Publish. | Title: "Zoom link updated for Saturday class" | Announcement created; only learners enrolled in that specific course see the notification/bulletin. | Medium | Functional / Positive | BRD-FR-I3, IMPLEMENTATION-pages-ops.js | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-060 | Admin Portal | Create New Course Division / Department | Admin logged in on #/divisions | 1. Click "Add Division". 2. Enter Name, Code, Division Head, and Description. 3. Click "Save". | Name: "Information Technology & AI", Code: "IT-AI", Head: "Dr. Tariq" | New division saved to divisions collection; displays in divisions data table. | Medium | Functional / CRUD | BRD-FR-A1, IMPLEMENTATION-pages-manage.js | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-061 | Admin Portal | Create Training Program under Division | Admin logged in on #/programs | 1. Click "Add Program". 2. Select Division: "IT-AI". 3. Enter Program Name, Code, Program Type (Diploma), and Duration. 4. Click "Save". | Type: Diploma, Duration: 6 Months, Code: DIP-AI | Program record created in programs collection with association to Division ID. | Medium | Functional / CRUD | BRD-FR-A1, BRD-FR-B6 | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-062 | Admin Portal | Course CRUD - Create Full Course with Zoom configuration | Admin logged in on #/manage/courses | 1. Click "Create Course". 2. Enter Code, Title, Tagline, Level, Program, Delivery (Hybrid). 3. Enter Zoom Register URL, Meeting ID, Passcode. 4. Set Status to Published. 5. Click Save. | Title: "Tableau for Data Visualization", Delivery: hybrid, Zoom details | Course saved to courses collection; appears on catalog and learner "My Courses" view. | High | Functional / CRUD | BRD-FR-A1, BRD-FR-A3, BRD-5 | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-063 | Admin Portal | Course CRUD - Edit Course Metadata and Accents | Admin on course builder #/manage/course/:id | 1. Open course editor. 2. Change tagline, accent color (#0f766e), and fee. 3. Click Save Changes. | Accent: #0f766e, Fee: 25000 | Course record updated in LocalStorage/Store; UI reflects new accent and fee instantly. | Medium | Functional / CRUD | IMPLEMENTATION-pages-manage.js | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-064 | Admin Portal | Course CRUD - Soft-delete / Archive Course | Admin on #/manage/courses | 1. Click delete/archive action on test course. 2. Confirm action in modal prompt. | Course: Test draft course | Course status changed to archived or record removed; course no longer appears in Learner active catalog. | Medium | Functional / CRUD | IMPLEMENTATION-pages-manage.js | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-065 | Admin Portal | Batch Creation and Management | Admin logged in on #/batches | 1. Click "New Batch". 2. Select Course, Assign Instructor, enter Venue/Online mode, Capacity (30), Start and End dates. 3. Save batch. | Course: "Tableau Analytics", Capacity: 30 | Batch saved under batches collection; linked correctly to course ID and instructor. | Medium | Functional / CRUD | BRD-FR-A1, BRD-FR-B6 | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-066 | Admin Portal | Manual Learner Enrollment into Batch/Course | Admin logged in on #/enrollments | 1. Click "Enroll Learner". 2. Select Learner from dropdown. 3. Select Course and Batch. 4. Choose Access Mode: "Full". 5. Click "Enroll". | Learner: learner@sdckarachi.org.pk, Mode: full | Enrollment record saved in enrollments; course immediately displays under Learner's "My Courses". | High | Functional / Positive | BRD-FR-A2, BRD-6.5 | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-067 | Admin Portal | Duplicate Enrollment Prevention | Admin logged in on #/enrollments | 1. Attempt to enroll the same learner into the exact same course/batch again. | Same Learner and Course ID | System alerts: "Learner is already enrolled in this course/batch"; duplicate record rejected. | Medium | Validation / Edge Case | IMPLEMENTATION-pages-manage.js | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-068 | Admin Portal | Learner Account Creation with Registration Number | Admin logged in on #/learners | 1. Click "Add Learner". 2. Enter Name, Email, Password, Phone, City, Reg No. 3. Click "Save". | Email: new.learner@gmail.com, RegNo: SDC-2026-REG-104 | Learner account created in users collection; password hashed with salt; role assigned as Learner. | High | Functional / CRUD | BRD-FR-A1, IMPLEMENTATION-pages-users.js | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-069 | Admin Portal | Instructor Account Creation with Specialization | Admin logged in on #/instructors | 1. Click "Add Instructor". 2. Fill Name, Email, Password, Designation, Specialization ("Data Analytics"). 3. Save record. | Role: Instructor, Designation: "Lead Corporate Trainer" | Instructor user created; role set to Instructor (base: teacher); appears in course assignment dropdowns. | High | Functional / CRUD | BRD-FR-A1, IMPLEMENTATION-pages-users.js | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-070 | Admin Portal | User Deletion constraint when records exist | Admin logged in on #/users | 1. Locate learner with active enrollments, submissions, or fee records. 2. Attempt to delete user. | User with dependent records | System prevents hard delete or prompts cascade confirmation; ensures orphaned records are not created. | Medium | Data Integrity | IMPLEMENTATION-pages-users.js, beforeDelete | PASS | Fixed: deleting a learner left fee records, messages and batch-instructor links behind. Accounts with fee records are now blocked from deletion ("set to Inactive instead"); messages and batch links are cleaned up with the other records. | Automated (tests/suite.run.js)
TC-071 | Admin Portal | Role & Permission Matrix Modification | Admin logged in on #/roles | 1. Select a custom role. 2. Check/uncheck permission box (e.g. announcements:create). 3. Save permissions matrix. | Action: Add announcements:create | Permissions object in roles collection updates; users with that role immediately gain/lose that permission. | High | Security / Permissions | IMPLEMENTATION-Roles & permissions | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-072 | Admin Portal | Built-in Admin Role Protection | Admin logged in on #/roles | 1. Attempt to delete or edit permissions for the default admin system role. | Role: admin | System locks role matrix for built-in admin; action is disabled; prevents system lockout. | High | Security / Business Logic | IMPLEMENTATION-Roles & permissions | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-073 | Operations | Fee Record Generation and Payment Status Update | Admin logged in on #/fees | 1. Click "Generate Fee Voucher". 2. Select Learner, Course, Amount, Due Date. 3. Save. 4. Later, click "Mark Paid", enter payment method (Bank Transfer) and transaction reference. 5. Save. | Amount: 15000, Method: Bank Transfer, Ref: TXN-98765 | Fee voucher status transitions from "Pending" to "Paid"; payment timestamp and reference saved. | Medium | Functional / CRUD | BRD-FR-A4, IMPLEMENTATION-pages-ops.js | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-074 | Operations | Results Calculation - Weighted Final Percentage Formula | Admin / Instructor on #/results | 1. Open Results calculation for a learner. 2. Enter Assessment marks: 80, Assignment Avg: 90, Attendance %: 100. 3. Inspect computed Final % based on Settings weights (e.g. 50% Assessment, 30% Assignment, 20% Attendance). | Weights: 50/30/20. Scores: 80, 90, 100 | Final % calculated exactly: (800.5) + (900.3) + (100*0.2) = 40 + 27 + 20 = 87%; assigned Grade 'A'. | High | Business Logic / Math | IMPLEMENTATION-Key flows (Results) | PASS | Weights are set in Settings > Learning. With 50/30/20 and scores 80/90/100 the final is 87%, grade A. | Automated (tests/suite.run.js)
TC-075 | Operations | Certificate Generation Eligibility Verification | Admin on #/certificates | 1. Check certificate eligibility list for learners in a course. 2. Verify whether learner with progress < 80% and failing result is eligible. | Progress: 50%, Failing grade | System flags learner as "Not Eligible"; issue certificate action is disabled. | High | Business Logic | BRD-BO-6, IMPLEMENTATION-Key flows (Certificates) | PASS | Fixed: a learner with a failing published result could still be issued a certificate if progress was high. A published result now decides eligibility; ineligible rows show "Not eligible" and cannot be selected. | Automated (tests/suite.run.js)
TC-076 | Operations | Issue Certificate and Generate Unique Code | Admin on #/certificates | 1. Select eligible learner with passing grade. 2. Click "Issue Certificate". 3. Verify generated certificate details. | Learner: Passed, Grade: 'A' | Certificate generated with sequential unique code (e.g. SDC-2026-0002); status set to "Valid"; saved in certificates. | High | Functional / CRUD | IMPLEMENTATION-Key flows (Certificates) | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-077 | Operations | Revoke Existing Certificate | Admin on #/certificates | 1. Locate an issued certificate. 2. Click "Revoke". 3. Enter revocation reason in confirmation modal. 4. Confirm. | Certificate: SDC-2026-0002 | Certificate status updates to "Revoked"; public verification on verify.html immediately flags it as Revoked. | High | Functional / Positive | IMPLEMENTATION-Key flows (Certificates) | PASS | Fixed: revoking now asks for a reason, saved with the certificate (revokeReason, revokedAt, revokedBy). verify.html shows the certificate as revoked. | Automated (tests/suite.run.js)
TC-078 | Operations | System Announcements broadcasting | Admin on #/announcements | 1. Create announcement with Audience: "Everyone" and priority "High". 2. Set pinned to true. 3. Publish. | Audience: everyone, Pinned: true | Announcement banner renders prominently on all dashboards (Admin, Instructor, Learner). | Medium | Functional / Positive | IMPLEMENTATION-pages-ops.js | PASS | Fixed: learners never saw pinned announcements on their home page (My Courses). Pinned announcements now show there as a banner; admin and instructor dashboards already showed them. | Automated (tests/suite.run.js)
TC-079 | Operations | In-app Direct Messaging between Users | Learner logged in on #/messages | 1. Click "New Message". 2. Select Instructor from recipient list. 3. Enter Subject and Message body. 4. Click Send. 5. Log in as Instructor and check #/messages. | Recipient: Instructor email | Message saved in messages collection; Instructor sees unread message indicator and received content. | Medium | Functional / Positive | BRD-1, IMPLEMENTATION-pages-ops.js | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-080 | Operations | Automated In-app Notifications on Assignment Submission | Learner submits an assignment | 1. Learner uploads assignment file for course. 2. Log in as assigned Course Instructor. 3. Inspect notification bell icon in top header. | New submission event | Notification icon shows unread count; dropdown lists "New submission received from [Learner Name]". | Medium | Functional / Notifications | IMPLEMENTATION-Key flows, core.js | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-081 | Operations | Operational Reports - Export Enrollments and Grades to CSV | Admin on #/reports | 1. Select Course Enrollment & Grade report. 2. Click "Export to CSV" button. | Action: CSV Download | Browser downloads properly formatted .csv file containing user names, registration numbers, courses, and marks. | Medium | Functional / Export | IMPLEMENTATION-core.js (CSV) | PASS | Fixed: the Enrollments and Results CSVs now include the registration number, and Results includes assignment %, assessment %, attendance %, final % and grade. | Automated (tests/suite.run.js)
TC-082 | Settings | Terminology Customization across application | Admin logged in on #/settings?tab=terms | 1. Open Terminology tab. 2. Change term for Learner from "Learner" to "Trainee". 3. Save Settings. 4. Inspect navigation menu and headers. | Key: learner -> Trainee | All UI labels using t('learner') dynamically re-render showing "Trainee" instead of "Learner". | Medium | Functional / Config | IMPLEMENTATION-Settings, Extensibility | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-083 | Settings | Grade Bands Configuration adjustment | Admin logged in on #/settings?tab=lms | 1. Open LMS Settings. 2. Adjust Grade 'A' minimum threshold from 80% to 85%. 3. Save settings. 4. Re-calculate student results scoring 82%. | Score: 82% | Grade recalculates to 'B+' instead of 'A', adhering to the newly updated grade band boundary. | Medium | Business Logic / Config | IMPLEMENTATION-Key flows (Results), Settings | PASS | Grade bands are free text in Settings > Learning. Default bands have no "B+", so 82% becomes B when A starts at 85%. Add "B+:80" to the bands to get B+. | Automated (tests/suite.run.js)
TC-084 | Settings | Reset to Default Demo Data | Admin logged in on #/settings?tab=general | 1. Scroll to Danger Zone. 2. Click "Reset Demo Data". 3. Confirm reset in confirmation modal prompt. | Action: Confirm Reset | Local storage sdcLearnDB_v1 is wiped and reseeded from seed.js; application reloads with fresh seed catalog. | High | Functional / Data | IMPLEMENTATION-Store API (resetDemoData) | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-085 | Data / UI Kit | Data Table Search, Sorting, and Pagination | Admin on #/learners with 25+ learner records | 1. Type name in table search filter. 2. Click "Name" column header to sort ASC/DESC. 3. Click page 2 pagination control. | Query: search keyword, sort toggle | Table filters rows instantly; sorts alphabetically without page reload; pagination displays correct slice of records. | Medium | UI / Data Table | IMPLEMENTATION-core.js (dataTable) | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-086 | Data / UI Kit | Modal confirmation dialog cancellation | User performs any destructive action (e.g. Delete record) | 1. Click delete icon on any record. 2. In the confirmation modal, click "Cancel" or press Escape key. | Action: Cancel delete | Modal closes; record remains completely intact in store; no changes committed. | Low | UI / Functional | IMPLEMENTATION-core.js (confirm) | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-087 | Performance & Sync | Debounced Cloud Sync to Supabase | User performs updates in rapid succession with cloud-sync.js enabled | 1. Edit a course title. 2. Edit description 2 seconds later. 3. Monitor network console. | Rapid store modifications | Multiple local saves trigger debounced sync; only the latest state snapshot is pushed to remote Supabase row. | Medium | Performance / Sync | IMPLEMENTATION-Architecture, cloud-sync.js | PASS | Saves are debounced (400 ms) and serialised; each push carries the latest full snapshot. | Automated (tests/suite.run.js)
TC-088 | Security | Passwords hashed with salt in LocalStorage | Inspect browser Application Storage after creating user | 1. Open Browser DevTools -> Application -> Local Storage. 2. Inspect sdcLearnDB_v1.users array. | User records in storage | All user records contain salt and passwordHash (iterated SHA-256); zero plaintext passwords exist in storage. | High | Security / Data Integrity | BRD-NFR-6, IMPLEMENTATION-Passwords | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-089 | Security | Server File Upload Security Headers and Validation | Direct API testing / UI inspection on Express backend | 1. Inspect server response headers on uploaded files via GET /uploads/<file>. | Upload file request | Server serves files with X-Content-Type-Options: nosniff and forces download to prevent arbitrary script execution. | High | Security / Backend | IMPLEMENTATION-Architecture, BRD-NFR-7 | PASS | Checked on the Express server: uploads are served with X-Content-Type-Options: nosniff and Content-Disposition: attachment, and .exe is rejected (415). On Vercel, files are served from Vercel Blob download URLs (forced download). | Automated (tests/suite.run.js)
TC-090 | Offline / Fallback | Offline file upload fallback to Data URL storage | Express backend is offline/stopped (server.js not running) | 1. Stop backend Express server. 2. Learner submits small assignment file (<2MB) via app.html#/submit. | Server unreachable | System falls back to inline Data URL storage; flags record stored: 'inline'; submission succeeds without crashing. | High | Resilience / Fallback | IMPLEMENTATION-Architecture, Key flows | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-091 | User Profile | Update User Profile Details and Password | Any logged-in user on #/profile | 1. Navigate to #/profile. 2. Update Phone Number and Bio. 3. Enter Current Password, New Password, Confirm New Password. 4. Click "Update Profile". | New Password: newSecurePassword!26 | Profile fields update; password hash updates; subsequent login requires the new password. | Medium | Functional / Positive | IMPLEMENTATION-pages-ops.js | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-092 | User Profile | Password update rejection on incorrect current password | User on #/profile attempting password change | 1. Enter wrong current password. 2. Enter matching new passwords. 3. Click "Change Password". | Incorrect current password | System alerts "Current password does not match"; password change is rejected. | Medium | Security / Validation | IMPLEMENTATION-pages-ops.js | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-093 | Schema Migration | Automatic store normalization on version bump | LocalStorage has missing properties or old schema version | 1. Load application with partial state missing divisions or progress. 2. Invoke application load. | Legacy/partial state | normalizeState() detects missing collections; injects defaults from seed; settings merged over DEFAULT_SETTINGS without data loss. | High | Data Integrity | IMPLEMENTATION-Data model, BRD-NFR-4 | PASS | Verified automatically. | Automated (tests/suite.run.js)
TC-094 | End-to-End Workflow | Full Learner Lifecycle: Enroll -> Attend -> Submit -> Grade -> Certificate | Complete multi-role workflow test | 1. Admin enrolls Learner in Excel course. 2. Learner accesses session and Zoom. 3. Learner submits assignment. 4. Instructor grades assignment. 5. Instructor marks attendance. 6. Admin publishes results and issues certificate. 7. Public verifies certificate on verify.html. | Full course test dataset | Complete workflow executes seamlessly across roles; certificate verifies successfully on public portal. | High | End-to-End | BRD-Executive summary, IMPLEMENTATION-Key flows | PASS | Verified automatically. | Automated (tests/suite.run.js)
|  |  |  | Unavailable course sessions should not be allowed to be marked as completed by learner. | [5 empty] | PASS | Fixed: learners can only mark a session complete once it has happened (status Available or Today). Upcoming, cancelled and postponed sessions show a note instead of the button, and the rule is enforced in Domain.setSessionComplete. Automated check TC-NEW-1. | Fix + automated check
|  |  |  | data leakage in supabase calls. Supabase data is accessible | [5 empty] | FIXED IN CODE - ACTION NEEDED | Confirmed: anyone holding the publishable key could read every user (emails, phones, password hashes) and overwrite the whole state. Fixed with a server gateway (backend/state-api.js): sign-in is checked on the server, a browser receives only its own password hash, learners can edit only their own profile, and accounts, roles and settings need the matching permission. Goes live once SDC_STATE_SECRET is set in Vercel and supabase/gateway.sql is run. | Fix + automated check
|  |  |  | Instructor should not have the authority to mark future or past attendances. Only admin should. | [5 empty] | PASS | Fixed: instructors can mark attendance only on the day of the session; past and future sessions are view-only with a note. Administrators can still correct any date. Automated checks TC-NEW-3 / TC-NEW-3b. | Fix + automated check
|  |  |  | Division should be auto selected upon selecting the program | [5 empty] | PASS | Fixed: choosing a program in the course form fills its division automatically. Automated check TC-NEW-4-5. | Fix + automated check
|  |  |  | End data of the course should be auto selected upon selecting the start data. end date should be calculated from the program duration | [5 empty] | PASS | Fixed: the course end date is filled from the start date plus the program duration (e.g. 1 Jan + "6 Months" = 30 Jun) and can still be edited. Automated check TC-NEW-4-5. | Fix + automated check
|  |  |  | Keep the duration either in program or in courses. | [5 empty] | PASS | Fixed: duration now lives only on the program. The course form no longer has its own duration field; course pages and certificates show the program duration. | Fix + automated check
Note on A16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The Token is nowhere to be found inside session or local browser storage. The session storage does contain a "sdcSession" variable which hold the value of "u-[firstname of user]" for example, [u-ali, u-faraz, u-admin]. Reply: If i login as a learner user and set the variable to 'u-admin', i will be logged in as an admin on page refresh.
Note on A29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The sessions on outline page should display detailed textual information of what is being taught in that session.
Note on A38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Opens an external link but a broken external link
Note on A40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Help button prompts the user to open outlook. No google form support.
Note on A50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Does not provide Batch start or end dates. All other are good.
Note on A53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Could not find Feedback section/modal/button
Note on A61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Adding a new session disrupts the existing course outline arrangement. It needs to be arranged manually
Note on A83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Does not give textbox to user for adding revocation reason, apart from that works as expected and shows up "revoked" when verified
Note on A100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Learner is created without Registration number or cnic Reply: Learner is enrolled in a course with no active batches available Reply: Enrolled learner is not appearing on the instructors portal.